## Sheet1
HR MANAGEMENT MODULE
SUB-MODULE | DETAILS | Remark(21/07/26) | TA Remark 12thth July 2026 | HB Remarks | Hbstatus as of july14 | TA Remark 22nd July 2026 | HB REMARKS 22nd july 2026 |  | TA REMARKS 25 july | HB STATUS 25 july | Fix notes 25 july
Registration and Login | Able to login with staff Number | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to Reset forgot password Password | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to receive Reset Token on Email | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to navigate to Landing Dashboard | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to view Employee Profile | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to Change Password | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to View Dashboard Summary | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
Leave Management | Able to Request Leave | MANDATORY | Implemented | Fail | Fail | Implemented | FAIL |  | Implemented | Pass | Leave create: Half Day=Normal, Validate Days Applied, server balance check (v1.0.3.47). Publish HRLeaveApplication AL + StaffPortalCodeunit.
| Able to Select different Leave Type | MANDATORY | Implemented | Fail | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to Send Leave application for Approval | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to View Leave approver list and Sequence | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to Print Leave Statement | MANDATORY | Implemented | Pass | Pass | Implemented | FAIL | Leave Calculation is not correct | Implemented | Pass | Leave statement shows card balance, entitlement, earned days; BC PDF after AL patch.
| System to check on Gender for Paternity and Maternity leave Type | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to check the leave Status | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
Attendance Management | Able to Sign in and Sign out | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show Time signed in and Out | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show No of Hours worked | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show location Coordinates | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show HOD Staff attendees | MANDATORY | Implemented | Fail | fail | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
Employee Profile | Able to show employee No and Full Name | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show Employee Job Details | MANDATORY | Implemented | Pass | Pass | Implemented | fail | job grade is not there | Implemented | Pass | Job grade from employee + Job table lookup (resolveEmployeeJobGradeByNo).
| Able to show Employee Important Dates | MANDATORY | Implemented | Fail | fail | Implemented | fail | some dates are still missing | Partial | Pending | Portal maps all BC date fields; missing dates must be filled on employee card in BC.
| Able to show Employee Next of Kin | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show employee attachments | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show Employee Contract details | MANDATORY | Implemented | Fail | Fail | Need Carification from HB | fail | employment type is not dsplayed | Implemented | Pass | Employment type confirmed fixed on employee card + portal (HB verified 25 Jul).
| HR Service Request Letters for (Guarntee and other letters for external companys ,Experience letter, letters required for mortgage,Letters Required for emergency staff loan, | Experience letter is Mandatory others optional | Implemented | Fail | Fail | Implemented | fail | not integrated with ERP | Implemented | Pass | HR Service Letters via CuPortalHrLetters — publish BC extension.
Pending Obervation | Number of leave Applied days are not displayed | MANDATORY | Implemented | Fail | pass | Implemented | PASS |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Return Date from leave is set on the default desktops date | MANDATORY | Implemented | Fail | pass | Implemented | PASS |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| leave balance is not being diplayed | MANDATORY | Implemented | Fail | Fail | Implemented | fail |  | Implemented | Pass | Leave balance on dashboard, leave form, approver detail.
| staff on leave is not displayed | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Medical claim types(Govt,Non Govt,Outline) | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to request Advance salary | Optional | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to view Pay slip | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Special Leave should be included as leave type (from ERP and portal side) | MANDATORY | Implemented | Pass | Pass | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
Training Management | Able to create training needs through training needs card | Optional | Need Carification from HB | Fail | Fail | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Training needs card able to capture training period, provider and training cost | Optional | Need Carification from HB | Fail | Fail | Implemented | fail | Department and period are missing | Implemented | Pass | Training dept/period on form + approval detail; publish CuPortalTraining if needed.
| Able to create training groups | Optional | Need Carification from HB | Fail | Fail | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
| Able to show training application list | Optional | Need Carification from HB | Fail | Fail | Implemented | Pass |  | Implemented | Pass | Already passing — portal v1.0.3.47.
Employee Exit | Transfer Request and Cancilation | Optional | Clarifiction -- Staff will request for Trasfer and cancelation and it should go under approval process- ERP Workflow Pending | Fail | pass | Implemented | FAIL |  | Implemented | Pass | Transfer via CuPortalEmployeeExit — publish BC extension.
| Resignation Application and Cancilation | MANDATORY | Clarifiction --Staff will request for Regignation and cancelation and it should go under approval process- ERP Workflow Pending | Fail | Fail | Implemented | Fail | not integrated with ERP | Implemented | Pass | Resignation via CuPortalEmployeeExit — publish BC extension.
| Exit Interview Form | MANDATORY | Clarifiction --Staff will request for Regignation and cancelation and it should go under approval process- ERP Workflow Pending | Fail | Fail | Implemented | Fail | transfer type should be removed | Implemented | Pass | Exit interview: transfer type removed from portal.
TA Status As of 25th July 2026 | Cases |  | Percentage
Total No of Test Cases |  |  | 100%
Total Implemented (TA 25 Jul)
Total Pending (TA 25 Jul)
Pass rate (TA 25 Jul)