## Executive Summary
HIJRA SSP UAT — Release evidence summary
Prepared 28 July 2026 • HR + Finance + Facility • all source rows, remarks, and Facility legacy comments included
Module | Test Rows | Bank Source Pass | Fix / Comment Fix | Out of Scope | Pending Live BC UAT
HR | 41 | 29 | 12 | 0 | 12
Finance | 42 | 22 | 20 | 0 | 20
Facility | 59 | 20 | 41 | 3 | 41
TOTAL | 142 | 71 | 73 | 3 | 73
Release verification
Backend TypeScript type-check | PASS
Portal on-prem production build | PASS
Automated backend tests | 75 PASS / 0 FAIL
Business Central AL object duplicate scan | 3,796 objects / 0 duplicate type+ID pairs
Live Business Central publish + UAT | PENDING — required before reporting all Pass
Do not submit this report as “all pass” yet. Update column L on the HR, Finance, and Facility tabs only after each live Business Central retest.

## HR
HIJRA SSP HR — Row-by-row UAT evidence
Source: /Users/abhishekbehera/Downloads/SSP HR HB Update Jul 26 2026 (2) (1).xlsx
Important: “Code fix implemented” means the local source/build checks passed. Enter Pass only after publishing the AL app and portal, then retesting against live Business Central.
Excel Row | Sub-module | Test Case / Details | Requirement / Priority | Latest TA Remark | Latest HB Status | All HB Remarks / Comments | Scope | Release Assessment | Implementation / Evidence | Verification Performed | Live UAT Retest | UAT Tester | UAT Date
3 | Registration and Login | Able to login with staff Number | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
4 | Registration and Login | Able to Reset forgot password Password | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
5 | Registration and Login | Able to receive Reset Token on Email | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
6 | Registration and Login | Able to navigate to Landing Dashboard | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
7 | Registration and Login | Able to view Employee Profile | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
8 | Registration and Login | Able to Change Password | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
9 | Registration and Login | Able to View Dashboard Summary | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Registration and Login workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
10 | Leave Management | Able to Request Leave | MANDATORY | Implemented | Fail | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: FAIL HB Status july27: Fail HB Remark july27: Canceled leave is considered as pending by the system and unable to modify requested leave( notify existence of pending leave) | In Scope | Code fix implemented | Leave status now comes from Business Central; cancelled leave is not treated as pending, and Open/Draft requests remain editable. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
11 | Leave Management | Able to Select different Leave Type | MANDATORY | Implemented | pass | HB Remarks: Fail Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Leave Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
12 | Leave Management | Able to Send Leave application for Approval | MANDATORY | Implemented | pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Leave Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
13 | Leave Management | Able to View Leave approver list and Sequence | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Leave Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
14 | Leave Management | Able to Print Leave Statement | MANDATORY | Implemented | fail | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: FAIL HB Status july27: fail HB Remark july27: Incorrect leave balance | In Scope | Code fix implemented | Leave request and leave statement use the same Business Central leave-balance resolver. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
15 | Leave Management | System to check on Gender for Paternity and Maternity leave Type | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Leave Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
16 | Leave Management | Able to check the leave Status | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Leave Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
17 | Attendance Management | Able to Sign in and Sign out | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Attendance Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
18 | Attendance Management | Able to show Time signed in and Out | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Attendance Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
19 | Attendance Management | Able to show No of Hours worked | MANDATORY | Implemented | pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Attendance Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
20 | Attendance Management | Able to show location Coordinates | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Attendance Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
21 | Attendance Management | Able to show HOD Staff attendees | MANDATORY | Implemented | Fail | HB Remarks: Fail Hbstatus as of july14: fail HB REMARKS 22nd july 2026: Pass HB Status july27: Fail | In Scope | Code fix implemented | HOD attendance is scoped to staff resolved through the supervisor/department relationship. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
22 | Employee Profile | Able to show employee No and Full Name | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Employee Profile workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
23 | Employee Profile | Able to show Employee Job Details | MANDATORY | Implemented | Fail | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: fail HB Status july27: Fail HB Remark july27: data integration mismuch(Unable to view correct department and division) | In Scope | Code fix implemented | Employee profile resolves HR employee data and Business Central department/division dimension aliases. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
24 | Employee Profile | Able to show Employee Important Dates | MANDATORY | Implemented | Fail | HB Remarks: Fail Hbstatus as of july14: fail HB REMARKS 22nd july 2026: fail HB Status july27: Fail HB Remark july27: informations are not correct(year of service) others missed to display the date(Last promotion & Retirement date) | In Scope | Code fix implemented | Years of service, last promotion date, and retirement date aliases/calculations are included. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
25 | Employee Profile | Able to show Employee Next of Kin | MANDATORY | Implemented | Pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Employee Profile workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
26 | Employee Profile | Able to show employee attachments | MANDATORY | Implemented | fail | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: fail HB Remark july27: next of kin Name is not displayes | In Scope | Code fix implemented | Next-of-kin name aliases are included in profile mapping; employee attachments remain available. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
27 | Employee Profile | Able to show Employee Contract details | MANDATORY | Implemented | Pass | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: fail HB Status july27: Pass | In Scope | Bank marked Pass — retained | Existing Employee Profile workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
28 | Employee Profile | HR Service Request Letters for (Guarntee and other letters for external companys ,Experience letter, letters required for mortgage,Letters Required for emergency staff loan, | Experience letter is Mandatory others optional | Implemented | Fail | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: fail HB Status july27: Fail HB Remark july27: no options for employees to get their own experience from SSP | In Scope | Code fix implemented | The existing Request Letters and standalone Emergency Staff Loan navigation are retained; experience, guarantee, external company, mortgage, emergency loan, and embassy forms remain wired to Business Central. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
29 | Pending Obervation | Number of leave Applied days are displayed | MANDATORY | Implemented | pass | HB Remarks: Fail Hbstatus as of july14: pass HB REMARKS 22nd july 2026: PASS HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
30 | Pending Obervation | Return Date from leave is set on the default desktops date | MANDATORY | Implemented | pass | HB Remarks: Fail Hbstatus as of july14: pass HB REMARKS 22nd july 2026: PASS HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
31 | Pending Obervation | leave balance is not being diplayed | MANDATORY | Implemented | pass | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: fail HB Status july27: pass HB Remark july27: mismuch leave balance between in the form and statement | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
32 | Pending Obervation | staff on leave is not displayed | MANDATORY | Implemented | Fail | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: Fail HB Remark july27: HOD are expected to see the active leave employees found under their supervision only | In Scope | Code fix implemented | Staff-on-leave is scoped to active leave for employees under the HOD/supervisor. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
33 | Pending Obervation | Medical claim types(Govt,Non Govt,Outline) | MANDATORY | Implemented | fail | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: fail | In Scope | Code fix implemented | Medical Claim is restored under HR with Government, Non-Government, and Outline/Online hospital categories. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
34 | Pending Obervation | Able to request Advance salary | Optional | Implemented | pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
35 | Pending Obervation | Able to view Pay slip | MANDATORY | Implemented | pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
36 | Pending Obervation | Special Leave should be included as leave type (from ERP and portal side) | MANDATORY | Implemented | pass | HB Remarks: Pass Hbstatus as of july14: Pass HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Pending Obervation workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
37 | Training Management | Able to create training needs through training needs card | Optional | Implemented | fail | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Pass HB Status july27: fail HB Remark july27: needs integration with ERP and the department field is inactive(shall be dropdown menu) | In Scope | Code fix implemented | Training now uses Business Central course and department lookups and saves the full training assessment. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
38 | Training Management | Training needs card able to capture training period, provider and training cost | Optional | Implemented | pass | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Pass HB Status july27: pass | In Scope | Bank marked Pass — retained | Existing Training Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
39 | Training Management | Able to create training groups | Optional | Implemented | Fail | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Pass HB Status july27: Fail HB Remark july27: able to include more than a single training per request | In Scope | Code fix implemented | Training supports a primary course plus additional training needs in one request. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
40 | Training Management | Able to show training application list | Optional | Implemented | fail | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Pass HB Status july27: fail | In Scope | Code fix implemented | Training application list/detail includes course, provider, department, period, budget, and Business Central status. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
41 | Employee Exit | Transfer Request and Cancilation | Optional | Implemented | Pass | HB Remarks: Fail Hbstatus as of july14: pass HB REMARKS 22nd july 2026: FAIL HB Status july27: Pass HB Remark july27: departments/branches has to be selected from only existed department and branch) and better to include in the menu of HR requests | In Scope | Bank marked Pass — retained | Existing Employee Exit workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
42 | Employee Exit | Resignation Application and Cancilation | MANDATORY | Implemented | Pass | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Fail HB Status july27: Pass HB Remark july27: Merge resignation request with exit interview | In Scope | Bank marked Pass — retained | Existing Employee Exit workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
43 | Employee Exit | Exit Interview Form | MANDATORY | Implemented | Pass | HB Remarks: Fail Hbstatus as of july14: Fail HB REMARKS 22nd july 2026: Fail HB Status july27: Pass HB Remark july27: Merge resignation request with exit interview | In Scope | Bank marked Pass — retained | Existing Employee Exit workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass

## Finance
HIJRA SSP FINANCE — Row-by-row UAT evidence
Source: /Users/abhishekbehera/Downloads/SSP Finance HB Update July 27 2026 (1) (1).xlsx
Important: “Code fix implemented” means the local source/build checks passed. Enter Pass only after publishing the AL app and portal, then retesting against live Business Central.
Excel Row | Sub-module | Test Case / Details | Requirement / Priority | Latest TA Remark | Latest HB Status | All HB Remarks / Comments | Scope | Release Assessment | Implementation / Evidence | Verification Performed | Live UAT Retest | UAT Tester | UAT Date
3 | Imprest Management | Able to perform Imprest Requisition under workflows | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
4 | Imprest Management | system shuolde not allow back or future imprest requistion/requred date (that must be the same with working date) | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
5 | Imprest Management | system shuolde not allow back date imprest requistion for start date | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
6 | Imprest Management | return date shoulde be the same or future date than from starting date | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
7 | Imprest Management | on imprest requistion duration date, department, responsibility center (job title),palce of duty,total net amount and the empoyee account number shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: 1. date of required is not displaye the correct date 2. travel date (start date ) is not linked with erp 3.requested amount is should be linked with daily rate that setup on erp 4.search bar is needed to find the requsition 5.travel destination is not linked with amount & should be available for writing HB Bank Remarks on 07/27/2026: fail comment: 1.daily rate is not displaying on both portal and ERP for per-diem and accomodation 2.daily rate is not populated from erp | In Scope | Code fix implemented | Imprest detail includes duration, dates, department, responsibility centre/job, place of duty, employee account, rates, and total. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
8 | Imprest Management | Able to add multiple Imprest lines | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
9 | Imprest Management | Able to Send Imprest Request for Approval | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
10 | Imprest Management | Able to Cancel wrong imprest request | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
11 | Imprest Management | Able to show approved Imprest/approval work flow | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: 1.duration date is must be available like (14/07/2026-20/7/2026) 2.when the approver reject the request the rejection reasone is must be available for requester HB Bank Remarks on 07/27/2026: fail comment: 1.duration date is must be available like (14/07/2026-20/7/2026) for approver 2.when the approver reject the request the rejection reasone is must be available for requester | In Scope | Code fix implemented | Approver detail includes travel dates/duration/destination; rejection remarks are returned to the requester. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
12 | Imprest Management | Able to Show Issues Imprest | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
13 | Imprest Management | Able to Show outstanding Imprest Amount | mandatory | Pending — Bank team to confirm which outstanding imprest amount to show. | fail | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: fail comment: outstanding amount w/c is not settled fully shoulde be displayed as remaining not settled amount for the requister | In Scope | Code fix implemented | Outstanding/unsettled imprest amount is derived and displayed from Business Central values. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
14 | Imprest Management | Able to show attachments | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Management workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
15 | Imprest Surrenders | Able to create New Surrender Request | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
16 | Imprest Surrenders | employee grade for surender should be available | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass comment: we need employee grade used for calculation of perdiem HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
17 | Imprest Surrenders | Able to attach supporting Document(all format) | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
18 | Imprest Surrenders | Able to partially Surrender | mandatory | Pending — Bank team to confirm how partial surrender should work. | pass | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
19 | Imprest Surrenders | on surended duration date, department, responsibility center (job title),palce of duty,empoyee account number shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: 1.duration date is should be available 2.travel destination is should be available 3.search bar is needed to fined imprest surrender HB Bank Remarks on 07/27/2026: fail comment: 1.duration date is should be available 2.travel destination is should be available | In Scope | Code fix implemented | Imprest surrender detail is enriched with the source imprest duration, destination, profile, and account information. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
20 | Imprest Surrenders | Able to Cancel wrong serender created | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
21 | Imprest Surrenders | the actual amount employee spend must be avilable on ERP | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
22 | Imprest Surrenders | edit option for serender request | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Imprest Surrenders workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
23 | Imprest Surrenders | Able to send for approval | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: search bar is needed for aproved document & reject document list HB Bank Remarks on 07/27/2026: fail comment: search bar is needed for aproved document & reject document list 2.travel duration date and travel destination shoulde be show for the aprover | In Scope | Code fix implemented | Surrender approval submission, approval detail, and searchable status lists are wired to Business Central. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
24 | Staff Claim to | Able to create new claim request | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass comment: search bar is needed for staff claim HB Bank Remarks on 07/27/2026: fail comment: we can not create new claim request | In Scope | Code fix implemented | Staff Claim header creation and employee department-code resolution are wired to Business Central. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
25 | Staff Claim to | system shuolde not allow back or future claim date (that must be the same with working date) | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Claim date is validated against the Business Central working date; back/future dates are rejected. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
26 | Staff Claim to | on staff claim duration date, department, responsibility center (job title),palce of duty,total net amount and the empoyee account number shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: we can not request other than medical refund HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Claim detail includes duration/date, department, responsibility centre/job, place of duty, employee account, and total. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
27 | Staff Claim to | on staff claim department, responsibility center (job title), total net amount and the empoyee account number shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Claim profile and financial detail are resolved from the authenticated Business Central employee and claim header. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
28 | Staff Claim to | for the medical claims hospital category and coverage percent shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Medical hospital category, coverage percentage, refund, and total fields are supported. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
29 | Staff Claim to | on staff claim line the claim type & account no must be linked | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Claim type drives the linked Business Central account selection/mapping. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
30 | Staff Claim to | Able to attach documents | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Claim document attachments use the portal attachment controller and Business Central document attachment table. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
31 | Staff Claim to | Able to show pending claims | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: requested staff calims is not displayed as one of separet item like imprest,surrender,purchase request on pending approval list HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Pending claim list uses Business Central status mapping. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
32 | Staff Claim to | Able to show Approved Claims | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Approved claim list uses Business Central status mapping. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
33 | Staff Claim to | able to delet claim lines | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Draft/Open claim lines can be deleted through the Business Central controller. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
34 | Staff Claim to | Able to Cancel wrong claim request (before approval ) | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | A wrong claim can be cancelled before approval. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
35 | Staff Claim to | Able to add multiple claim lines | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Multiple claim lines are supported end to end. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
36 | Petty Cash | Able to create New Petty Cash Request | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
37 | Petty Cash | system shuolde not allow back or future petty cash Needed date (that must be the same with working date) | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
38 | Petty Cash | on petty cash requistion department, responsibility center ,total net amount and the empoyee account number shoulde be availabel | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail comment: 1.employee information shoulde have alignment with employee profile HB Bank Remarks on 07/27/2026: fail comment: 1.employee information shoulde have alignment with employee profile | In Scope | Code fix implemented | Petty-cash detail uses the authenticated employee department, responsibility centre, account, and total. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
39 | Petty Cash | Able to add and show attachments | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
40 | Petty Cash | petty cash limit depend on department | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | Department petty-cash limit lookup/display is included. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
41 | Petty Cash | Able to Cancel wrong petty cash request (before approval ) at all | mandatory | Implemented | fail | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: fail | In Scope | Code fix implemented | A wrong petty-cash request can be cancelled before approval. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
42 | Petty Cash | Able to add multiple Petty cash Lines | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: pass HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
43 | Petty Cash | Able to send Petty cash request for Approval | mandatory | Implemented | pass | HB Bank Remarks on 07/18/2026: fail HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
44 | Petty Cash | 1.petty cash repleshiment is used for request petty cash so rename by petty cash request 2.petty cash request is used for settlement so rename by petty cash settlement |  | Implemented | pass | HB Bank Remarks on 07/27/2026: pass | In Scope | Bank marked Pass — retained | Existing Petty Cash workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass

## Facility
HIJRA SSP FACILITY — Row-by-row UAT evidence
Source: /Users/abhishekbehera/Downloads/SSP Facility HB July 21 2026.xlsx
Important: “Code fix implemented” means the local source/build checks passed. Enter Pass only after publishing the AL app and portal, then retesting against live Business Central.
Excel Row | Sub-module | Test Case / Details | Requirement / Priority | Latest TA Remark | Latest HB Status | All HB Remarks / Comments | Scope | Release Assessment | Implementation / Evidence | Verification Performed | Live UAT Retest | UAT Tester | UAT Date
3 | Purchases | Able to create new Purchase requisition | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Purchases workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
4 | Purchases | Abel to add specificiton of item FA/Service | Mandatory | Implemented | fail | HB Remarks: fail Remark: we can add the specification but generate as discription & no attached specification documents Legacy Excel comment: Tesfaye Tolcha Gemeda: we can add the specification but generate as description & no attached specification documents | In Scope | Code fix implemented | Purchase lines expose Specification / Description and purchase attachments accept specification documents. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
5 | Purchases | Able to add multiple line | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Purchases workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
6 | Purchases | Able to send request for Approval | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Purchases workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
7 | Purchases | Able cancel purchase approval request | Mandatory | Implemented | pass | HB Remarks: pass Remark: the PR at approver side cahanged to Purchase Qote Legacy Excel comment: Tesfaye Tolcha Gemeda: approver cannot see the request | In Scope | Comment-driven fix implemented | Purchase requisition approval cancellation stays mapped to the PR document instead of a Purchase Quote. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
8 | Purchases | Abel to see pending purchase reuqest | Mandatory | Implemented | pass | HB Remarks: pass Remark: the PR at approver side cahanged to Purchase Qote Legacy Excel comment: Tesfaye Tolcha Gemeda: approver cannot see the PR; it appears as Purchase Quote and details change | In Scope | Comment-driven fix implemented | Pending Purchase Requisition approval detail is read through the PR mapping, not the Purchase Quote presentation. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
9 | Purchases | Abel to approve pending request | Mandatory | Implemented | pass | HB Remarks: pass Remark: the PR at approver side cahanged to Purchase Qote Legacy Excel comment: Tesfaye Tolcha Gemeda: approver cannot see the PR; it appears as Purchase Quote and details change | In Scope | Comment-driven fix implemented | Purchase Requisition approval actions retain the PR number, lines, requester, and attachment context. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
10 | Purchases | Abel to Generate purchase requisitons report | Mandatory | Not in SSP, It should generate from ERP | fail | HB Remarks: fail Remark: requisitor cant see the detail of the requested item at SSP | In Scope | Code fix implemented | Requester detail includes purchase lines and specifications; the formal printable report remains an ERP output. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
11 | Stores | Able to create new store request | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
12 | Stores | Able to check item availability | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
13 | Stores | Able to show issued stock | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
14 | Stores | Able to add more Store requisition line | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
15 | Stores | Abel to get receiptient confirmation of received from requisitor | Mandatory | Implemented | fail | HB Remarks: fail Remark: not generate confirmation/request for confirmation for the requested item | In Scope | Code fix implemented | Store requisition supports recipient receive confirmation against issued quantities. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
16 | Stores | Able to send store requisition for approval | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
17 | Stores | Abel to see pending store requisiton for apprval | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
18 | Stores | Abel to Generate store requisitons report | Mandatory | Not in SSP, It should generate from ERP | fail | HB Remarks: fail Remark: what about the requisitor the requisitor needs to see the detail request against issue | In Scope | Code fix implemented | Store detail shows requested, issued, received, and outstanding quantities. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
19 | Stores | Abel to approve/cancel store requesition | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Stores workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
20 | Fuel | Able to create new Fuel request | Can be pend | Implemented | pass | HB Remarks: pass Legacy Excel comment: Tesfaye Tolcha Gemeda: integrate vehicle plate number with the specific fuel card number | In Scope | Comment-driven fix implemented | Fuel-card lookup now returns and displays its assigned vehicle plate/vendor linkage. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
21 | Fuel | Able to check fuel availability | Can be pend | Clarification with Bank | fail | HB Remarks: fail Remark: Need to check fuel request standard against the request fuel /km for each vehicle fuel request | In Scope | Code fix implemented | Fuel detail includes vehicle/card linkage and odometer/standard information for comparison. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
22 | Fuel | Able to show issued Fuel(approved fuel requests) | Can be pend | Implemented | fail | HB Remarks: fail Remark: it does not show the requested detail & with approver side it shows as FLT maintenance request | In Scope | Code fix implemented | Fuel and maintenance approval documents are separated by request/document type; issued fuel detail is shown. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
23 | Fuel | Able to send Fuel requisition for approval | Can be pend | Implemented | fail | HB Remarks: fail Remark: it does not show the requested detail & with approver side it shows as FLT maintenance request | In Scope | Code fix implemented | Fuel approval submission retains fuel type and full request detail. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
24 | Fuel | Abel to see pending fuel request | Can be pend | Implemented | fail | HB Remarks: fail Remark: it does not show the requested detail & with approver side it shows as FLT maintenance request | In Scope | Code fix implemented | Pending fuel list/detail uses the Business Central fuel status and request type. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
25 | Fuel | Able to create new Fuel request | Can be pend | Implemented | pass | HB Remarks: pass Remark: can creat still not show the requested line | In Scope | Bank marked Pass — retained | Existing Fuel workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
26 | Fuel | Able to send Fuel requisition for approval | Can be pend | Implemented | fail | HB Remarks: fail Remark: it does not show the requested detail & with approver side it shows as FLT maintenance request | In Scope | Code fix implemented | Fuel approval submission and approver detail use the fuel mapping rather than maintenance. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
27 | Transport | Able to send request City Transport request | Mandatory | Implemented | pass | HB Remarks: pass Legacy Excel comment: Tesfaye Tolcha Gemeda: need trip starting/from and employee name | In Scope | Comment-driven fix implemented | Transport includes Trip Origin / Starting From and resolves the internal employee passenger name. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
28 | Transport | Able to request FieldTransport request | Mandatory | Implemented | fail | HB Remarks: fail Remark: its outomatically changed to as city request when sent to approval Legacy Excel comment: Tesfaye Tolcha Gemeda: need trip starting/from and employee name; only City trip is recognized | In Scope | Code fix implemented | Field Trip is explicitly mapped as a distinct Business Central option and is not converted to City. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
29 | Transport | Abel to add Line for External and internals passangers list | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Transport workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
30 | Transport | Able Line Manager approves city /Field request | Mandatory | Implemented | fail | HB Remarks: fail Remark: its outomatically changed to as city request when sent to approval Legacy Excel comment: Tesfaye Tolcha Gemeda: approver cannot see the Field Trip request | In Scope | Code fix implemented | Approver detail preserves Field Trip and exposes origin, destination, trip dates, and passengers. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
31 | Transport | Able Reject City/field Transport Request | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Transport workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
32 | Transport | Abel Cancel City/field Transport Request | Mandatory | Clarification with Bank | pass | HB Remarks: pass Remark: It can be rejected we have tested with reject | In Scope | Bank marked Pass — retained | Existing Transport workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
33 | Transport | Able to receive request for reschedule proposed due to Vehicle unavailability | Mandatory | Implemented | pass | HB Remarks: pass | In Scope | Bank marked Pass — retained | Existing Transport workflow retained; no module or navigation removal is included in this release. | Source workbook is marked Pass; full portal/backend regression build passed. | Bank source says Pass
34 | Transport | Prevent duplicate Vehicle Request | Mandatory | ERP Pending | fail | HB Remarks: fail Remark: not prevent duplicate vehile request | In Scope | Code fix implemented | Duplicate vehicle/trip validation is retained in the Business Central-connected transport flow. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
35 | Maintenance | Create Fixed Asset maintenance request by user organ | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance Request is restored with asset, priority, odometer, service, and description fields. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
36 | Maintenance | Send maintenance for approval | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance requests can be submitted to the approval workflow. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
37 | Maintenance | Abel to approve pending request | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Pending maintenance requests appear in the approval queue/detail. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
38 | Maintenance | reject mainenance rquest | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance requests can be rejected through approvals with remarks. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
39 | Maintenance | Technical Manager assigns internal technician | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance detail/controller includes technician assignment fields. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
40 | Maintenance | Requestor confirm receipt of maintained FA | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance detail/controller includes requester receipt confirmation. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
41 | Maintenance | Create request for vehicle service maintenance at ≥5,000 km and submit | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Vehicle maintenance captures current/last/next odometer values for the 5,000 km rule. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
42 | Maintenance | Abel to show next maintenance KM. | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Next maintenance kilometre is saved and displayed. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
43 | Maintenance | Abel to reject maintenance request | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance rejection is available through the shared approval workflow. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
44 | Maintenance | Abel to aprove requested maintenance | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | In Scope | Code fix implemented | Maintenance approval is available through the shared approval workflow. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
45 | Work Ticket | Creat A requistion for booking | Mandatory | Out Of Scope | fail | HB Remarks: fail Remark: not have required field to fill the flight booking | In Scope | Code fix implemented | Work Tickets / Flight Booking is restored with traveler, route, dates, class, airline, and justification. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
46 | Work Ticket | Request sent for approval | Mandatory | Out Of Scope | fail | HB Remarks: fail Remark: not have required field to fill the flight booking | In Scope | Code fix implemented | Work-ticket flight booking has a dedicated Business Central approval request action. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
47 | Work Ticket | Request approved/ rejected | Mandatory | Out Of Scope | fail | HB Remarks: fail Remark: not have required field to fill the flight booking | In Scope | Code fix implemented | Work-ticket approvals are mapped to table 50866 and appear in the approval decision screen. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
48 | Work Ticket | Booking confirmaiton receipt | Mandatory | Out Of Scope | fail | HB Remarks: fail Remark: not have required field to fill the flight booking | In Scope | Code fix implemented | Booking confirmation/reference can be recorded against the work ticket. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
49 | Transfer order | Able to create Handover of vehicle and tools | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Asset / Vehicle / Tool Transfer is a separate module; it no longer reuses Transfer Order. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
50 | Transfer order | Able to approve handover of vehicle | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Asset-transfer approval maps to Business Central table 50278. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
51 | Transfer order | Able to do temporary asset transfer to employee | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Temporary/permanent transfer, employee, and expiry fields are included. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
52 | Transfer order | Able to approve temporary asset transfer list | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Temporary asset transfer appears in the approval workflow. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
53 | Transfer order | Able to Cancel temporary asset transfer list | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Asset-transfer approval can be cancelled before completion. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
54 | Transfer order | Able to post asset transfer | Mandatory | Implemented | fail | HB Remarks: fail Remark: the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | In Scope | Code fix implemented | Approved asset transfer exposes the post action through the dedicated controller. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
55 | Gate Pass | Able to request Goods, maintained goods, with Gate Pass | Mandatory | Implemented | fail | HB Remarks: fail Remark: The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | In Scope | Code fix implemented | Gate Pass supports Store Issue, Transfer Order, and Asset Transfer source references. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
56 | Gate Pass | Able to approve gate pass | Mandatory | Implemented | fail | HB Remarks: fail Remark: The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | In Scope | Code fix implemented | Gate Pass approval retains the source document linkage. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
57 | Gate Pass | Able to reject gate pass | Mandatory | Implemented | fail | HB Remarks: fail Remark: The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | In Scope | Code fix implemented | Gate Pass rejection retains the source document linkage. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
58 | Gate Pass | Able Generate Gate Pass Log Report | Mandatory | Not in SSP, It should generate from ERP | fail | HB Remarks: fail Remark: The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | In Scope | Code fix implemented | Portal Gate Pass log/detail is available; the formal printable report remains an ERP output. | Backend type-check passed; on-prem portal build passed; 75 automated backend tests passed. | Pending live BC UAT
59 | Procurment Individual Budget Prepartion | Able Department or district enters to budget template | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | Out of Scope | Out of Scope — confirmed | Procurement Individual Budget Preparation is excluded from the requested portal scope; no deployment requirement. | Scope confirmed from the workbook and user instruction. | Not Required
60 | Procurment Individual Budget Prepartion | Able to itemized procurement budget plan | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | Out of Scope | Out of Scope — confirmed | Procurement Individual Budget Preparation is excluded from the requested portal scope; no deployment requirement. | Scope confirmed from the workbook and user instruction. | Not Required
61 | Procurment Individual Budget Prepartion | Able to submits itemized procurement budget plan | Can be pend | Out Of Scope | fail | HB Remarks: fail Remark: the template not there at SSP | Out of Scope | Out of Scope — confirmed | Procurement Individual Budget Preparation is excluded from the requested portal scope; no deployment requirement. | Scope confirmed from the workbook and user instruction. | Not Required