## Sheet1
FACILITY MANAGEMENT MODULE — UAT STATUS DOCUMENTATION
SUB-MODULE | DETAILS | TA Remark 11th July 2026 | Pilot Rollout Priority | HB Result 14th July 2026 | HB Remark / Comment 14th July 2026 | TA REMARKS 28th July 2026 | HB Bank Result after deployment | comment / implementation note
Purchases | Able to create new Purchase requisition | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to add specificiton of item FA/Service | Implemented | Mandatory | fail | we can add the specification but generate as discription & no attached specification documents | Implemented | Pending UAT | Dedicated specification field and request attachments are included.
| Able to add multiple line | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to send request for Approval | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able cancel purchase approval request | Implemented | Mandatory | pass | the PR at approver side cahanged to Purchase Qote | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to see pending purchase reuqest | Implemented | Mandatory | pass | the PR at approver side cahanged to Purchase Qote | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to approve pending request | Implemented | Mandatory | pass | the PR at approver side cahanged to Purchase Qote | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to Generate purchase requisitons report | Not in SSP, It should generate from ERP | Mandatory | fail | requisitor cant see the detail of the requested item at SSP | Implemented — ERP report | Pending UAT | Portal request details and lines are included; the formal requisition report remains an ERP output.
Stores | Able to create new store request | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to check item availability | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to show issued stock | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to add more Store requisition line | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to get receiptient confirmation of received from requisitor | Implemented | Mandatory | fail | not generate confirmation/request for confirmation for the requested item | Implemented | Pending UAT | Recipient confirmation and post-receipt action are included.
| Able to send store requisition for approval | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to see pending store requisiton for apprval | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel to Generate store requisitons report | Not in SSP, It should generate from ERP | Mandatory | fail | what about the requisitor the requisitor needs to see the detail request against issue | Implemented — ERP report | Pending UAT | Request detail shows requested, issued, received, and outstanding quantities; the formal report remains an ERP output.
| Abel to approve/cancel store requesition | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
Fuel | Able to create new Fuel request | Implemented | Can be pend | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to check fuel availability | Clarification with Bank | Can be pend | fail | Need to check fuel request standard against the request fuel /km for each vehicle fuel request | Implemented | Pending UAT | Vehicle fuel-standard comparison and odometer/standard fields are included.
| Able to show issued Fuel(approved fuel requests) | Implemented | Can be pend | fail | it does not show the requested detail & with approver side it shows as FLT maintenance request | Implemented | Pending UAT | Fuel and maintenance requests are separated by document type, with complete fuel details.
| Able to send Fuel requisition for approval | Implemented | Can be pend | fail | it does not show the requested detail & with approver side it shows as FLT maintenance request | Implemented | Pending UAT | Fuel approval mapping and full request details are included.
| Abel to see pending fuel request | Implemented | Can be pend | fail | it does not show the requested detail & with approver side it shows as FLT maintenance request | Implemented | Pending UAT | Pending fuel status, request type, and detail mapping are included.
| Able to create new Fuel request | Implemented | Can be pend | pass | can creat still not show the requested line | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to send Fuel requisition for approval | Implemented | Can be pend | fail | it does not show the requested detail & with approver side it shows as FLT maintenance request | Implemented | Pending UAT | Fuel approval mapping and full request details are included.
Transport | Able to send request City Transport request | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to request FieldTransport request | Implemented | Mandatory | fail | its outomatically changed to as city request when sent to approval | Implemented | Pending UAT | Field Transport is explicitly mapped and preserved when submitted for approval.
| Abel to add Line for External and internals passangers list | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able Line Manager approves city /Field request | Implemented | Mandatory | fail | its outomatically changed to as city request when sent to approval | Implemented | Pending UAT | Approval details preserve City versus Field Transport request type.
| Able Reject City/field Transport Request | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Abel Cancel City/field Transport Request | Clarification with Bank | Mandatory | pass | It can be rejected we have tested with reject | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Able to receive request for reschedule proposed due to Vehicle unavailability | Implemented | Mandatory | pass |  | Implemented | Pending UAT | Previously passed by HB; retain as a regression check after deployment.
| Prevent duplicate Vehicle Request | ERP Pending | Mandatory | fail | not prevent duplicate vehile request | Implemented | Pending UAT | Duplicate vehicle/trip validation is included in the Business Central-connected flow.
Maintenance | Create Fixed Asset maintenance request by user organ | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Send maintenance for approval | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Abel to approve pending request | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| reject mainenance rquest | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Technical Manager assigns internal technician | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Requestor confirm receipt of maintained FA | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Create request for vehicle service maintenance at ≥5,000 km and submit | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Abel to show next maintenance KM. | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Abel to reject maintenance request | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Abel to aprove requested maintenance | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
Work Ticket | Creat A requistion for booking | Out Of Scope | Mandatory | fail | not have required field to fill the flight booking | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Request sent for approval | Out Of Scope | Mandatory | fail | not have required field to fill the flight booking | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Request approved/ rejected | Out Of Scope | Mandatory | fail | not have required field to fill the flight booking | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Booking confirmaiton receipt | Out Of Scope | Mandatory | fail | not have required field to fill the flight booking | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
Transfer order | Able to create Handover of vehicle and tools | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | A separate Asset Transfer module is included; this is not the Transfer Order workflow.
| Able to approve handover of vehicle | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | Vehicle/tool handover approval mapping is included.
| Able to do temporary asset transfer to employee | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | Temporary transfer includes employee, transfer type, and expiry fields.
| Able to approve temporary asset transfer list | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | Temporary Asset Transfer approval workflow is included.
| Able to Cancel temporary asset transfer list | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | Temporary Asset Transfer cancellation is included.
| Able to post asset transfer | Implemented | Mandatory | fail | the test case is for Asset Transfer/Vehicle or tools the SSP is Transfer order which is different | Implemented | Pending UAT | Approved-only Asset Transfer posting is included end to end.
Gate Pass | Able to request Goods, maintained goods, with Gate Pass | Implemented | Mandatory | fail | The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | Implemented | Pending UAT | Gate Pass source selection and Store/Transfer/Asset reference integration are included.
| Able to approve gate pass | Implemented | Mandatory | fail | The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | Implemented | Pending UAT | Gate Pass approval retains the linked source document reference.
| Able to reject gate pass | Implemented | Mandatory | fail | The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | Implemented | Pending UAT | Gate Pass rejection retains the linked source document reference.
| Able Generate Gate Pass Log Report | Not in SSP, It should generate from ERP | Mandatory | fail | The gate pass not generate the transferd /Store issued/maintained with specific refernce need to integrate | Implemented — ERP report | Pending UAT | The portal Gate Pass log view is included; the formal printable report remains an ERP output.
Procurment Individual Budget Prepartion | Able Department or district enters to budget template | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Able to itemized procurement budget plan | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
| Able to submits itemized procurement budget plan | Out Of Scope | Can be pend | fail | the template not there at SSP | Out Of Scope | N/A | Excluded from the agreed UAT scope; no SSP portal template or test execution is required.
TA Status As on 12th July 2026 | Cases | Percentage
Total No of Test Cases | 59 | 100%
Total No of Test Cases Implemented | 36 | 63%
Total No of Test Cases Pending | 22 | 37%
Status tested by HB as of July 14, 2026
TA Status As on 12th July 2026 | Cases | Percentage
Total No of Test Cases | 59 | 100%
Total No of Test Cases pass | 20 | 33.9%
Total No of Test Cases fail | 39 | 66.1%
FACILITY UAT DOCUMENTATION STATUS AS OF 28 JULY 2026
Measure | Cases | Percentage / Status
Total test cases | 59 | 100%
In-scope test cases | 42 | 71.19%
Implemented and locally verified | 42 | 100%
Out Of Scope — excluded | 17 | 28.81%
Pending live UAT after deployment | 42 | 100%
Important: “Implemented” means the release contains the fix and local verification passed. HB must update the post-deployment result to Pass or Fail after live UAT.