## SSP_Facility_HB
FACILITY MANAGEMENT |  |  |  | TA Remark (Updated 27 Jun 2026) | ERP / BC Action Required
SUB-MODULE | DETAILS | TA Remark 26th Jun 2026 | HB Remarks
Purchases | Able to create new Purchase requisition | Implemented
| Abel to add specificiton of item FA/Service | Implemented |  | Implemented
| Able to add multiple line | Implemented |  | Implemented
| Able to send request for Approval | Implemented |  | Implemented
| Able cancel purchase approval request | Implemented |  | Implemented | Enable Purchase Requisition approval workflow in BC if submit fails.
| Abel to see pending purchase reuqest | Implemented |  | Implemented
| Abel to approve pending request | Implemented |  | Implemented
| Abel to Generate purchase requisitons report | N/A |  | Implemented
Stores | Able to create new store request | Implemented |  | N/A | Purchase requisition report is BC report object; not in portal scope.
| Able to check item availability |  |  | Implemented
| Able to show issued stock | Implemented |  | Pending | Expose item stock per location in BC OData (QyItems/QyInventory) for line-level availability check.
| Able to add more Store requisition line | Implemented |  | Implemented | Quantity Issued comes from BC after store posting/issue.
| Abel to get receiptient confirmation of received from requisitor |  |  | Implemented
| Able to send store requisition for approval | Implemented |  | Partial | Portal has Receive line + Post to receive (ReceiveStoreLineItems). Needs BC posting/issue flow and Posted status in UAT.
| Abel to see pending store requisiton for apprval | Implemented |  | Implemented
| Abel to Generate store requisitons report | Implemented |  | Implemented
| Abel to approve/cancel store requesition | Implemented |  | Implemented | Store usage report reads QyStoreRequisitionLines.
Fuel | Able to create new Fuel request |  |  | Implemented | Approve/reject via BC approval entries.
| Able to check fuel availability |  |  | Partial | Portal UI + SOAP wired (FnFuelRequisitionHeader). UAT blocked until BC fuel cards, vehicles, vendors, and approval workflow are configured.
| Able to show issued Fuel(approved fuel requests) |  |  | Pending | BC must publish fuel balance/availability OData per card or vehicle tank.
| Able to send Fuel requisition for approval |  |  | Pending | BC must expose issued/approved fuel history OData for portal list.
| Abel to see pending fuel request |  |  | Partial | Same as fuel create/submit above.
| Able to create new Fuel request |  |  | Partial | Fuel list uses QyFuelMaintenanceRequests filter RequestType 0/3.
| Able to send Fuel requisition for approval |  |  | Partial | Duplicate row in HB sheet — same fuel create status as row 21.
Transport | Able to send request City Transport request | Implemented |  | Partial | Duplicate row in HB sheet — same fuel approval status as row 24.
| Able to request FieldTransport request |  |  | Implemented | City transport (RequestType 0).
| Abel to add Line for External and internals passangers list | Implemented |  | Partial | Field trip UI + SOAP RequestType 1 built; UAT pending BC workflow/number series.
| Able Line Manager approves city /Field request |  |  | Implemented | Staff + External passengers via TransportRequisitionPassenger.
| Able Reject City/field Transport Request |  |  | ERP only | Line Manager approval is BC workflow/approval user setup — portal exposes approve/reject on approval entry.
| Abel Cancel City/field Transport Request |  |  | ERP only | Reject is BC approval action — portal Approvals page supports it when entry is open.
| Able to receive request for reschedule proposed due to Vehicle unavailability |  |  | Partial | Cancel wired (CancelTransportRequisition). Confirm in UAT.
| Prevent duplicate Vehicle Request |  |  | Pending | No portal UI/API for transport reschedule — needs BC SOAP/OData spec from HB.
Maintenance | Create Fixed Asset maintenance request by user organ |  |  | Pending | Duplicate prevention not implemented in portal; needs BC validation rule or API.
| Send maintenance for approval |  |  | Partial | Maintenance create UI + FnFuelRequisitionHeader RequestType 1 built; UAT pending.
| Abel to approve pending request |  |  | Partial | Submit wired (FnFuelRequisitionApprovalAction).
| reject mainenance rquest |  |  | ERP only | Approver assignment + BC workflow configuration.
| Technical Manager assigns internal technician |  |  | ERP only | Reject via BC approval entry.
| Requestor confirm receipt of maintained FA |  |  | Pending | Technician assignment is BC role/action — no portal screen yet.
| Create request for vehicle service maintenance at ≥5,000 km and submit |  |  | Pending | Requestor receipt confirmation not built — needs BC SOAP method.
| Abel to show next maintenance KM. |  |  | Partial | Vehicle service type (RequestType 2) + odometer fields in UI; ≥5000 km rule validation needs BC or portal rule.
| Abel to reject maintenance request |  |  | Pending | Next maintenance KM display needs BC calculated field/OData.
| Abel to aprove requested maintenance |  |  | ERP only | Reject via BC approval.
Work Ticket | Creat A requistion for booking |  |  | ERP only | Approve via BC approval.
| Request sent for approval |  |  | Pending | Work ticket booking create not built — only list/detail/delete line (QyWorkTickets).
| Request approved/ rejected |  |  | Pending | No work-ticket submit SOAP wired.
| Booking confirmaiton receipt |  |  | Pending | No work-ticket approval in portal.
Transfer order | Able to create Handover of vehicle and tools |  |  | Pending | Booking confirmation receipt not built.
| Able to approve handover of vehicle |  |  | Pending | Vehicle handover module marked Coming Soon — no backend SOAP wired.
| Able to do temporary asset transfer to employee | Implemented |  | Pending | Depends on vehicle handover module + BC workflow.
| Able to approve temporary asset transfer list | Implemented |  | Implemented | Transfer Order create/approve/cancel/post path exists.
| Able to Cancel temporary asset transfer list | Implemented |  | Implemented | Approval via TransferOrderApproval + Approvals page.
| Able to post asset transfer | Implemented |  | Implemented | Cancel via TransferOrderApproval cancelApproval.
Gate Pass | Able to request Goods, maintained goods, with Gate Pass |  |  | Partial | Post/receipt may require BC action after approval — confirm Transfer Order posting in UAT.
| Able to approve gate pass |  |  | Partial | Gate pass list + approval from BC-generated docs (store issue / transfer order). Asset transfer creation blocked Coming Soon.
| Able to reject gate pass |  |  | Partial | RequestGatePassApproval wired; needs BC gate pass records created from issued store/transfer docs.
| Able Generate Gate Pass Log Report |  |  | ERP only | Reject via BC approval entry on gate pass.
Procurment Individual Budget Prepartion | Able Department or district enters to budget template |  |  | Implemented | Gate Pass Log report at /reports/gate-pass-log.
| Able to itemized procurement budget plan |  |  | Pending | Procurement Individual Budget module not in portal — needs HB BC spec/API.
| Able to submits itemized procurement budget plan |  |  | Pending | Itemized procurement budget plan not in portal.
|  |  |  | Pending | Budget plan submit not in portal.
TA Status As on 26th June 2026 | Cases | Percentage |  | TA Status (Updated 27 Jun 2026) | Count
Total No of Test Cases | 59 | 100% |  | Total No of Test Cases | 59
Total No of Test Cases Implemented |  |  |  | Implemented (portal) | 22
Total No of Test Cases Pending |  |  |  | Partial (portal built, UAT/BC pending) | 16
|  |  |  | Pending (not built on portal) | 17
|  |  |  | ERP only (BC admin/workflow) | 4
|  |  |  | N/A | 1
|  |  |  | Portal completion (Implemented+Partial) | 64.4