## SSP_Facility_HB
FACILITY MANAGEMENT — UAT STATUS (Technology Associates)
SUB-MODULE | DETAILS (HB test case) | HB Original Remark | HB Remarks | TA UAT Status (27 Jun 2026) | Owner | Actual issue / evidence | Action required
Purchases | Able to create new Purchase requisition | Implemented |  | Implemented | — | Purchase header creates in BC (req 1326, 1332). | None.
| Abel to add specificiton of item FA/Service | Implemented |  | Blocked | BC Admin | Add line fails: Vendor Posting Group does not exist (service TRAINING EXPENSE on req 1326). | Complete vendor posting setup on the BC vendor used by purchase requisitions.
| Able to add multiple line | Implemented |  | Blocked | BC Admin | Cannot add second line until row 4 vendor posting is fixed. | Same as above.
| Able to send request for Approval | Implemented |  | Pending | BC Admin + Portal | Cannot submit for approval until lines exist. Portal fix: approval history hidden while Open (needs build after 27-Jun ZIP). | Fix vendor posting; redeploy latest portal; retest Request Approval.
| Able cancel purchase approval request | Implemented |  | Not retested | — | Cancel flow not exercised in this UAT session. | Retest after purchase lines work.
| Abel to see pending purchase reuqest | Implemented |  | Not retested | — | Approver pending list not exercised for purchase in this session. | Retest with HOD user after lines work.
| Abel to approve pending request | Implemented |  | Not retested | — | Approve action not exercised for purchase in this session. | Retest with approver after submit works.
| Abel to Generate purchase requisitons report | N/A |  | N/A | N/A | BC report object; not in self-service portal scope. | Use BC client for reports.
Stores | Able to create new store request | Implemented |  | Implemented | — | Store requisition header creates. | None.
| Able to check item availability | Need Discussion |  | Need Discussion | HB | Item availability check not built in portal. | Confirm if required in portal or BC only.
| Able to show issued stock | Implemented |  | Implemented | — | Issued stock view works per prior UAT. | None.
| Able to add more Store requisition line | Implemented |  | Implemented | Portal + User | Lines add for Item type. Asset type: portal now clears item when switching to Asset (user must pick FA from asset list, not item 10). | Redeploy latest portal; users pick fixed asset from asset dropdown.
| Abel to get receiptient confirmation of received from requisitor | N/A |  | N/A | N/A | Recipient confirmation not in portal scope. | BC process if required.
| Able to send store requisition for approval | Implemented |  | Implemented | — | Store submit for approval works when lines valid. | None.
| Abel to see pending store requisiton for apprval | Implemented |  | Implemented | — | Pending store requisitions visible to approver. | None.
| Abel to Generate store requisitons report | Implemented |  | Implemented | — | Store report available in BC; portal lists requests. | None.
| Abel to approve/cancel store requesition | Implemented |  | Implemented | — | Approve/cancel store requisition works. | None.
Fuel | Able to create new Fuel request |  |  | Implemented | Portal | Fuel list returned HTTP 500 — fixed (OData filter removed; in-memory type filter). | Redeploy 27-Jun ZIP or later.
| Able to check fuel availability |  |  | Not retested | — | Fuel availability display not verified this session. | Retest on HIJRA.
| Able to show issued Fuel(approved fuel requests) |  |  | Not retested | — | Issued fuel list not verified this session. | Retest on HIJRA.
| Able to send Fuel requisition for approval |  |  | Blocked | BC Admin | Request Approval fails: approval workflow not configured (BC table 50865). | Enable fuel approval workflow in Business Central.
| Abel to see pending fuel request |  |  | Not retested | — | Pending fuel queue not verified this session. | Retest after workflow enabled.
| Able to create new Fuel request |  |  | Duplicate | — | Duplicate of row 20 in HB sheet. | Count once only in summary.
| Able to send Fuel requisition for approval |  |  | Duplicate | — | Duplicate of row 23 in HB sheet. | Count once only in summary.
Transport | Able to send request City Transport request | Implemented |  | Blocked | BC Admin | Create transport fails: TR number series / blank transport number record. | Repair Transport Requisition number series in BC; remove blank-number record.
| Able to request FieldTransport request |  |  | Blocked | BC Admin | Field transport cannot be tested until header create works. | Fix TR number series first.
| Abel to add Line for External and internals passangers list | Implemented |  | Not retested | — | Passenger lines not tested — header create blocked. | Retest after transport create works.
| Able Line Manager approves city /Field request |  |  | Not retested | — | Line manager approve not tested this session. | Retest after transport submit works.
| Able Reject City/field Transport Request |  |  | Not retested | — | Reject not tested this session. | Retest after transport submit works.
| Abel Cancel City/field Transport Request |  |  | Not retested | — | Cancel not tested this session. | Retest after transport submit works.
| Able to receive request for reschedule proposed due to Vehicle unavailability |  |  | Not retested | — | Reschedule flow not tested this session. | Retest when transport module stable.
| Prevent duplicate Vehicle Request |  |  | Not retested | — | Duplicate prevention not tested this session. | Retest when transport module stable.
Maintenance | Create Fixed Asset maintenance request by user organ |  |  | Implemented | — | Maintenance header creates (e.g. L00040). List empty for some users may mean no records yet or filter. | None.
| Send maintenance for approval |  |  | Blocked | BC Admin | Request Approval fails: approval workflow not configured for maintenance. | Enable maintenance approval workflow in BC (table 50865).
| Abel to approve pending request |  |  | Blocked | BC Admin | Approver actions depend on BC workflow. | Enable maintenance workflow.
| reject mainenance rquest |  |  | Blocked | BC Admin | Reject depends on BC workflow. | Enable maintenance workflow.
| Technical Manager assigns internal technician |  |  | Not in portal | HB | Technician assignment is BC workflow; not in ESS portal. | Confirm BC process.
| Requestor confirm receipt of maintained FA |  |  | Not in portal | HB | Receipt confirmation not in portal scope. | Confirm BC process.
| Create request for vehicle service maintenance at ≥5,000 km and submit |  |  | Not retested | — | Vehicle service at 5000km not tested this session. | Retest after workflow enabled.
| Abel to show next maintenance KM. |  |  | Not retested | — | Next maintenance KM display not verified. | Retest on HIJRA.
| Abel to reject maintenance request |  |  | Blocked | BC Admin | Reject depends on BC workflow. | Enable maintenance workflow.
| Abel to aprove requested maintenance |  |  | Blocked | BC Admin | Approve depends on BC workflow. | Enable maintenance workflow.
Work Ticket | Creat A requistion for booking |  |  | Blocked | HB/BC Dev | Create fails: SOAP method 'WorkTicketHeader' is invalid on HIJRA CuStaffPortal. | ESS has list/delete only. HB must publish correct create SOAP or confirm create not supported.
| Request sent for approval |  |  | N/A | N/A | Blocked until work ticket create exists in BC. | See row 45.
| Request approved/ rejected |  |  | N/A | N/A | Blocked until work ticket create exists in BC. | See row 45.
| Booking confirmaiton receipt |  |  | N/A | N/A | Blocked until work ticket create exists in BC. | See row 45.
Transfer order | Able to create Handover of vehicle and tools |  |  | Implemented | — | Transfer order header, lines, submit work (e.g. TO 1055). | None.
| Able to approve handover of vehicle |  |  | Partial | BC Admin + Portal | Status shows Pending Approval but QyApprovalEntry may be empty. Portal shows approvers only after submit; placeholder if BC has no entries. | BC: verify approval workflow table 5740; redeploy latest portal.
| Able to do temporary asset transfer to employee | Implemented |  | Implemented | — | Asset transfer (vehicle/tools handover) create works. | None.
| Able to approve temporary asset transfer list | Implemented |  | Implemented | — | Asset transfer approval works when BC workflow configured. | None.
| Able to Cancel temporary asset transfer list | Implemented |  | Implemented | — | Cancel asset transfer works. | None.
| Able to post asset transfer | Implemented |  | Implemented | — | Post asset transfer works. | None.
Gate Pass | Able to request Goods, maintained goods, with Gate Pass |  |  | Not retested | — | Gate pass create/submit not in this retest batch. | Retest on HIJRA.
| Able to approve gate pass |  |  | Not retested | — | Gate pass approve not retested. | Retest on HIJRA.
| Able to reject gate pass |  |  | Not retested | — | Gate pass reject not retested. | Retest on HIJRA.
| Able Generate Gate Pass Log Report |  |  | N/A | N/A | Gate pass log report is BC report. | Use BC client.
Procurment Individual Budget Prepartion | Able Department or district enters to budget template |  |  | N/A | N/A | Procurement budget not in self-service portal. | Out of scope.
| Able to itemized procurement budget plan |  |  | N/A | N/A | Procurement budget not in self-service portal. | Out of scope.
| Able to submits itemized procurement budget plan |  |  | N/A | N/A | Procurement budget not in self-service portal. | Out of scope.
SUMMARY (excludes duplicate fuel rows 25–26)
Total unique test cases | 57 | 100%
Implemented | 15 | 26.32%
Partial (portal + BC) | 1 | 1.75%
Blocked (BC / HB config) | 11 | 0.193
Not retested this session | 17 | 0.2982
Need Discussion | 1 | 0.0175
Not in portal / N/A | 11 | 0.193
CONFIRMED UAT ISSUES LOG — 27 Jun 2026
# | Module | Symptom | Root cause | Owner | Evidence / doc no. | Portal fix? | Action
1 | Purchase Requisition | Add line fails | Vendor has no Vendor Posting Group in BC | BC Admin | Req 1326, item TRAINING EXPENSE | No — BC master data | Complete vendor posting setup; retry line
2 | Purchase Requisition | Approval history visible while Open | Portal showed QyApprovalEntry before submit | Portal | Req 1332 | Yes — fixed after 27-Jun AM ZIP | Redeploy latest portal build
3 | Transport Requisition | Create header fails | TR number series / blank number record | BC Admin | City transport form 27-Jun | No | Repair TR no. series in BC
4 | Fuel Request | List API HTTP 500 | OData RequestType filter incompatible with HIJRA schema | Portal | GET /api/requests?module=fuelRequest | Yes — in 27-Jun ZIP | Redeploy if not on latest build
5 | Fuel / Maintenance | Request Approval fails | Approval workflow not configured (table 50865) | BC Admin | Maintenance L00040 | No | Enable workflow in BC
6 | Maintenance Request | List shows no records | May be empty filter or no rows for user; create works | — | Screenshot empty list; L00040 created | N/A | Retest list after create
7 | Work Ticket | Create fails | SOAP WorkTicketHeader invalid — not published on HIJRA | HB/BC Dev | AnyDesk 27-Jun | Portal added create; ESS has no create | HB confirm SOAP name or disable create
8 | Store Requisition | Asset line rejected by BC | User sent item 10 as Asset; not a Fixed Asset | User + Portal | Item 10 - LAPTOP | Yes — clear item on type change | User picks FA from asset list
9 | Transfer Order | Approval history empty when Pending | BC may not write QyApprovalEntry for table 5740 | BC Admin + Portal | TO 1055 | Partial — broader lookup + placeholder | BC verify workflow; redeploy portal
PORTAL DEPLOY NOTE
Package: SelfServiceSuite-UAT-2026-06-27-client-full-offline.zip (AM build).
Additional fixes AFTER that ZIP: purchase approval history on Open, store asset line, transfer approval lookup.
Run: bash deploy/create-full-offline-suite.sh for a fresh ZIP with all portal fixes.
Deploy: stop-suite → extract → keep .env → start-suite → Ctrl+F5 on http://10.30.4.23:4000