## HR Status
Sub-Module | Test Case / Details | TA Status (27 Jun 2026) | ERP / BC Action Required | Owner
Registration and Login | Able to login with staff Number | Implemented |  | TA
Registration and Login | Able to Reset forgot password Password | Implemented |  | TA
Registration and Login | Able to receive Reset Token on Email | Partial | BC must deliver reset email from employee card; portal calls FnResetPassword | BC
Registration and Login | Able to navigate to Landing Dashboard | Implemented |  | TA
Registration and Login | Able to view Employee Profile | Implemented | /profile — bio, job, kin, contract, attachments | TA
Registration and Login | Able to Change Password | Implemented |  | TA
Registration and Login | Able to View Dashboard Summary | Implemented |  | TA
Leave Management | Able to Request Leave | Implemented |  | TA
Leave Management | Able to Select different Leave Type | Implemented | Types from QyHRLeaveType OData | TA+BC
Leave Management | Able to Send Leave application for Approval | Implemented | BC leave approval workflow must be enabled | BC
Leave Management | Able to View Leave approver list and Sequence | Implemented | RequestProgress / BC approval entries | TA+BC
Leave Management | Able to Print Leave Statement | Implemented | /hr/leave-statement PDF | TA
Leave Management | System to check on Gender for Paternity and Maternity leave Type | Implemented | Portal filters leave types by employee gender | TA
Leave Management | Able to check the leave Status | Implemented |  | TA
Attendance Management | Able to Sign in and Sign out | Implemented | FnCheckinCheckout; HTTP-safe stable device ID (Jun-27) | TA
Attendance Management | Able to show Time signed in and Out | Implemented |  | TA
Attendance Management | Able to show No of Hours worked | Partial | Displayed when BC populates HoursWorked on QyAttendanceLedger | BC
Attendance Management | Able to show location Coordinates | Implemented | Portal shows MAC Address (device fingerprint / optional Windows MAC helper) | TA
Attendance Management | Able to show HOD Staff attendees | Implemented | HOD team attendance table; Staff on Leave at /hod/staff-on-leave | TA
Employee Profile | Able to show employee No and Full Name | Implemented |  | TA
Employee Profile | Able to show Employee Job Details | Implemented |  | TA
Employee Profile | Able to show Employee Important Dates | Implemented |  | TA
Employee Profile | Able to show Employee Next of Kin | Implemented |  | TA
Employee Profile | Able to show employee attachments | Implemented | /api/profile/attachments | TA
Employee Profile | Able to show Employee Contract details | Implemented |  | TA
Employee Profile | HR Service Request Letters for (Guarntee and other letters for external companys ,Experience letter, letters required for mortgage,Letters Required for emergency staff loan, | Partial | Document Requisition UI exists; nav marked Coming Soon; backend SOAP not wired — needs HB BC spec | TA+BC
Employee Profile | Transfer Request and Cancilation | Pending | Coming Soon in portal; needs HB BC transfer workflow + OData/SOAP spec | TA+BC
Employee Profile | Resignation Application and Cancilation | Pending | Coming Soon in portal; needs HB BC resignation workflow + spec | TA+BC
Employee Profile | Exit Interview Form | Pending | Not in portal; ESS has QyExitInterviewForm — needs HB spec | TA+BC
Employee Profile | Number of leave Applied days are not displayed | Implemented | DaysApplied shown on leave list and detail | TA
Employee Profile | Return Date from leave is set on the default desktops date | Partial | Portal uses BC FnGetLeaveDates; verify BC leave calendar if date wrong | BC
Employee Profile | leave balance is not being diplayed | Implemented | Balance shown on leave form via getLeaveBalance API | TA+BC
Employee Profile | staff on leave is not displayed | Partial | HOD Staff on Leave page built; not on employee leave screen | TA
pend | Medical claim types(Govt,Non Govt,Outline) | Implemented | Staff Claims (Finance) — Govt / Private / Online hospital categories | TA
pend | Able to request Advance salary | Implemented | /hr/salary-advance | TA
pend | Able to view Pay slip | Implemented | /hr/payslip PDF via BC | TA+BC
pend | Special Leave should be included as leave type (from ERP and portal side) | Partial | Portal loads all QyHRLeaveType codes; BC must publish Special Leave | BC
Training Management | Able to create training needs through training needs card | Partial | Basic Training Request (course + comments); not full ESS needs card | TA+BC
Training Management | Training needs card able to capture training period, provider and training cost | Pending | Fields not in portal; needs HB BC field/SOAP mapping | TA+BC
Training Management | Able to create training groups | Pending | Not in portal; needs HB spec | TA+BC
Training Management | Able to show training application list | Implemented | QyTrainingApplicationHeader on /hr/training-request | TA
TA Status As on 27th June 2026 | Cases | Percentage
Total No of Test Cases | 41 | 1
Total No of Test Cases Implemented
Total No of Test Cases Partial
Total No of Test Cases Pending

## Summary
Metric | Value
Total test cases | 41
Implemented | 29
Partial (portal built, UAT/BC pending) | 7
Pending (not built) | 5
Portal coverage (Implemented + Partial) | 87.8%
Latest UAT ZIP | SelfServiceSuite-UAT-2026-06-27-client-full-offline.zip
ERP mapping source | src/staffModules.ts, src/portalApi.ts, src/erpMappings.ts
Jun-27 portal fixes relevant to HR HB
Attendance | Coordinates requirement replaced with MAC Address; stable sign-in on HTTP
Leave | DaysApplied, balance, gender filter, return dates via BC APIs
Auth | Forgot/reset password with BC active-user check
HOD | Staff on Leave, team attendance, department staff list
BC / HB still required
Transfer / Resignation / Exit Interview | Workflow + OData/SOAP specs from HB
Document Requisition letters | Backend module + approval workflow
Training needs card / groups | Field mapping and BC pages
Special Leave | Publish leave type in QyHRLeaveType

## ERP Mapping
Portal Module | OData / API | SOAP / Action | BC Table / Notes | Portal Route
Login / Auth | QyPortalUser, QyHREmployee | FnAuthenticateUser, FnResetPassword | — | /login, /forgot-password
Leave Requisition | QyHRLeaveApplications | FnSaveLeaveApplication, RequestLeaveApproval, CancelLeave | Leave ledger | /hr/leave-request
Leave balance / dates | QyHRLeaveLedger, QyHRLeaveType | FnGetLeaveBalance, FnGetLeaveDates | — | Leave form APIs
Leave Statement | QyHRLeaveApplications | GenerateLeaveStatement (PDF) | — | /hr/leave-statement
Attendance | QyAttendanceLedger | FnCheckinCheckout | MAC sent in Location field | /hr/attendance
Employee Profile | QyHREmployee, QyEmployeeKin, etc. | — | Profile OData | /profile
Salary Advance | QyStaffAdvanceHeader | FnStaffAdvanceHeader, approval SOAP | — | /hr/salary-advance
Payslip | QyPayrollPeriod | GeneratePayslip PDF SOAP | — | /hr/payslip
Staff Claims (Medical) | QyStaffClaimHeader/Lines | Staff claim SOAP | Hospital category Govt/Private/Online | /finance/staff-claim
Training Request | QyTrainingApplicationHeader | FnTrainingRequest, TrainingApproval | — | /hr/training-request
Document Requisition | — | Not wired | Awaiting HB spec | /hr/document-requisition (Coming Soon)
Employee Transfer | — | Not wired | Awaiting HB spec | /hr/employee-transfer (Coming Soon)
Employee Resignation | — | Not wired | Awaiting HB spec | /hr/employee-resignation (Coming Soon)
Exit Interview | QyExitInterviewForm (ESS only) | Not in portal | Awaiting HB spec | —
HOD Staff on Leave | QyHRLeaveApplications | Filter posted leave | — | /hod/staff-on-leave
HOD Team Attendance | QyAttendanceLedger | — | Today filter | /hr/attendance (HOD view)